## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Developer | 2025-10-31 | Staff creation failed when email was left empty | Sprint-2 | Developer | Standards | Added email null and blank validation in backend | 2025-11-01 | Closed | Fixed and tested using Postman
2 | Developer | 2025-11-02 | Duplicate staff email was allowed | Sprint-2 | Developer | Logical | Added duplicate email check in repository layer | 2025-11-03 | Closed | Retested with JUnit
3 | Developer | 2025-11-14 | Stock creation failed for negative unit value | Sprint-3 | Developer | Standards | Added unit > 0 validation in StockController | 2025-11-15 | Closed | Working as expected
4 | Developer | 2025-11-20 | JWT token not generated on first login attempt | Sprint-4 | Developer | Logical | Fixed JWT filter configuration and token generation logic | 2025-11-21 | Closed | Login tested successfully
5 | Developer | 2025-11-22 | Frontend not loading stock data initially | Sprint-4 | Developer | User Interface | Fixed API integration issue in frontend | 2025-11-23 | Closed | Data loading correctly
6 | Developer | 2025-11-04 | API returned 500 error when updating non-existing staff ID | Sprint-2 | Developer | Logical | Added proper ID check and error handling in update API | 2025-11-05 | Closed | Error resolved and verified
7 | Developer | 2025-11-06 | Stock update API accepted invalid negative unit value | Sprint-2 | Developer | Standards | Added validation to reject negative unit values | 2025-11-07 | Closed | Retested using JUnit
8 | Developer | 2025-11-16 | Email notification was not triggered after order creation | Sprint-3 | Developer | Logical | Fixed email service method call after successful order creation | 2025-11-17 | Closed | Email received successfully
9 | Developer | 2025-11-24 | Frontend login failed when JWT token expired | Sprint-4 | Developer | User Interface | Added token expiry handling and auto logout logic | 2025-11-25 | Closed | Session handling works correctly
10 | Developer | 2025-11-26 | UI not showing validation message for empty stock fields | Sprint-4 | Developer | User Interface | Added frontend form validation for empty inputs | 2025-11-27 | Closed | User-friendly validation added
11 | Developer | 2025-11-18 | API response time slow for stock list API | Sprint-3 | Developer | Maintainability | Optimized database query and reduced unnecessary logs | 2025-11-19 | Closed | Performance improved
12 | Developer | 2025-11-19 | Duplicate stock entries allowed with same product name | Sprint-3 | Developer | Logical | Added duplicate product name check in service layer | 2025-11-20 | Closed | Duplicate prevention working
13 | Developer | 2025-10-30 | Login API accepted empty username | Sprint-2 | Developer | Standards | Added null and empty validation for username | 2025-10-31 | Closed | Validated using Postman
14 | Developer | 2025-11-28 | Unauthorized access allowed for stock APIs without JWT | Sprint-4 | Developer | Standards | Secured stock APIs using JWT authentication filter | 2025-11-29 | Closed | Access control verified
15 | Developer | 2025-11-01 | Incorrect error message returned for invalid login credentials | Sprint-2 | Developer | Logical | Updated authentication error handling logic | 2025-11-02 | Closed | Correct message displayed
16 | Developer | 2025-11-21 | Order creation failed when stock quantity was insufficient | Sprint-3 | Developer | Logical | Added stock availability check before order creation | 2025-11-22 | Closed | Order flow works correctly
17 | Developer | 2025-11-29 | Frontend page reload required after stock update | Sprint-4 | Developer | User Interface | Fixed state refresh after successful update | 2025-11-30 | Closed | Data updates dynamically
18 | Developer | 2025-11-17 | API returned empty response for valid stock list | Sprint-3 | Developer | Standards | Fixed repository query mapping issue | 2025-11-18 | Closed | Correct data returned
19 | Developer | 2025-11-30 | Session not invalidated after logout | Sprint-4 | Developer | Standards | Implemented token invalidation logic on logout | 2025-11-30 | Closed | Logout works as expected

## Sheet2
Logical
User Interface
Maintainability
Standards
Others